CAPSTONE PROJECT REPORT

Report 2 – Project Management Plan

IceBot – Design and Implementation of a Multi-Location Automated Vending System with Robotic Arm Integration

– Ho Chi Minh, May 2026 –

Table of Contents

I. Record of Changes	3

II. Project Management Plan	4

1. Overview	4

1.1 Scope & Estimation	4

1.2 Project Objectives	4

1.3 Project Risks	4

2. Management Approach	5

2.1 Project Process	5

2.2 Quality Management	5

2.3 Training Plan	5

3. Project Deliverables	5

4. Responsibility Assignments	5

5. Project Communications	6

6. Configuration Management	6

6.1 Document Management	6

6.2 Source Code Management	6

6.3 Tools & Infrastructures	6

# I. Record of Changes

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 26/5/2026 | A |  | scope & estimation, tools & infractures, project objectives, time frame, sponsor, customer, constraints, training plan. |

*A - Added M - Modified D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Scope & Estimation

| # | WBS Item | Complexity | Est. Effort (man-days) |
| --- | --- | --- | --- |
| 1 | Feature 1: Authentication |  | 4 |
| 1.1 | Function 1.1: Login for admin and organization’s admin | Simple | 1 |
| 1.2 | Function 1.2: Change password | Simple | 1 |
| 1.3 | Function 1.3: Profile view and edit | Simple | 1 |
| 1.4 | JWT authentication integration with web, mobile, and kiosk clients | Simple | 1 |
| 2 | Feature 2: User & Role Management |  | 5 |
| 2.1 | Function 2.1: Create/update/deactivate and view staff/manager/admin accounts | Simple | 1 |
| 2.2 | Function 2.1: Assign roles and permissions by organizations or kiosk location | Simple | 1 |
| 2.3 | Function 2.3: Search, filter, sort and paginate records | Simple | 1 |
| 2.4 | Function 2.4: Audit important account and permission change | Simple | 1 |
| 2.5 | Function 2.5: Invitation and notification support for newly created account | Simple | 1 |
| 3 | Feature 3: Organization & Location Owner Management |  | 6 |
| 3.1 | Function 3.1: Create and manage business organization operation kiosks | Simple | 1 |
| 3.2 | Function 3.2: Register and manage machine placement locations | Simple | 1 |
| 3.3 | Function 3.3: Manage access time, availability, and basic location information | Simple | 1 |
| 3.4 | Function 3.4: Track revenue or commission for location owners | Simple | 1 |
| 3.5 | Function 3.5: View location-based kiosk activity and usage reports | Simple | 1 |
| 3.6 | Function 3.6: Configure location-level operating policies | Simple | 1 |
| 4 | Feature 4: Kiosk & Machine Management |  | 12 |
| 4.1 | Function 4.1: Create, update, view and delete kiosks reports | Simple | 1 |
| 4.2 | Function 4.2: Assign kiosk to organization, manager, staff and location owner | Simple | 1 |
| 4.3 | Function 4.3: Manage kiosk operating schedule and availability status | Simple | 1 |
| 4.4 | Function 4.4: Synchronize configuration from cloud backend to edge gateway | Complex | 5 |
| 4.5 | Function 4.5: Track kiosk status: online, offline, unavailable, maintenance, or error | Simple | 1 |
| 4.6 | Function 4.6: Manage kiosk devices: robot arm, dispenser, sensors | Medium | 3 |
| 4.7 | Function 4.7: Export/setup kiosk configuration for edge server installation | Simple | 1 |
| 5 | Feature 5: Device, Robot & Sensor Management |  | 12 |
| 5.1 | Function 5.1: Create device types and models for robot arm, dispenser, sensors, relay, and I/O modules | Simple | 1 |
| 5.2 | Function 5.2: Register Fairino robot controller and Ethernet/RJ45 connection data | Medium | 3 |
| 5.3 | Function 5.3: Monitor sensors: position, ingredient level, camera, emergency stop, and safety status | Medium | 3 |
| 5.4 | Function 5.4: Store and view device function/parameter definitions | Simple | 1 |
| 5.5 | Function 5.5: Manage robot task status: idle, processing, completed, paused, failed | Simple | 1 |
| 5.6 | Function 5.6: Integrated device health telemetry and error reporting | Simple | 1 |
| 5.7 | Function 5.7: Support device replacement and configuration validation | Simple | 1 |
| 5.8 | Function 5.8: Record device logs for trouble shooting and maintenance | Simple | 1 |
| 6 | Feature 6: Catalogue & Menu Management |  | 7 |
| 6.1 | Function 6.1: Create, update delete and view ice cream products | Simple | 1 |
| 6.2 | Function 6.2: Manage flavours, toppings, and ingredients proportion | Simple | 1 |
| 6.3 | Function 6.3: Assign menus to selected kiosks or locations | Simple | 1 |
| 6.4 | Function 6.4: Manage product availability based on inventory and machine capability | Simple | 1 |
| 6.5 | Function 6.5: Configure pricing and promotions for managers | Simple | 1 |
| 6.6 | Function 6.6: Display product catalogue on kiosk app and admin dashboard | Simple | 1 |
| 6.7 | Function 6.7: Validate product constraints against robot workflow requirements | Simple | 1 |
| 7 | Feature 7: Workflow Management System |  | 13 |
| 7.1 | Function 7.1: Create and update robot workflow preparation for products | Medium | 2 |
| 7.2 | Function 7.2: Define workflow steps such as cup pickup, ice cream dispensing, topping addition, and pickup delivery | Complex | 4 |
| 7.3 | Function 7.3: View simulation and workflow details and step parameters | Medium | 2 |
| 7.4 | Function 7.4: Validation and verify workflow simulation steps | Simple | 1 |
| 7.5 | Function 7.5: Map workflow steps to Fairino SDK commands or edge action | Medium | 2 |
| 7.6 | Function 7.6: Validate safety rules before executing robot actions | Simple | 1 |
| 7.7 | Function 7.7: Versions workflows to avoid breaking active kiosks | Simple | 1 |
| 8 | Feature 8: Customer Ordering System |  | 7 |
| 8.1 | Function 8.1: Browse ice cream products on kiosk app | Simple | 1 |
| 8.2 | Function 8.2: Customize order by flavour, topping | Simple | 1 |
| 8.3 | Function 8.3: Create order and send order data to backend | Simple | 1 |
| 8.4 | Function 8.4: Track order status from pending payment to robot preparation and pickup | Simple | 1 |
| 8.5 | Function 8.5: Handle cancellation and unavailable-product cases | Simple | 1 |
| 8.6 | Function 8.6: Provide user-friendly kiosk UI for unattended retail | Simple | 1 |
| 8.7 | Function 8.7: Support local Kiosk behaviour when network is unstable | Simple | 1 |
| 9 | Feature 9: Payment Integration |  | 8 |
| 9.1 | Function 9.1: Create payment sessions for order using QR code | Simple | 1 |
| 9.2 | Function 9.2: Update payment status through webhook | Simple | 1 |
| 9.3 | Function 9.3: Store payment transaction and receipt information | Medium | 2 |
| 9.4 | Function 9.4: Protect payment flow with validation and authorization | Medium | 2 |
| 9.5 | Function 9.5: Support card/e-wallet payment design for future integration | Medium | 2 |
| 10 | Feature 10: Edge Gateway/ Robot Arm Integration |  | 5 |
| 10.1 | Function 10.1: Build edge gateway/edge server | Simple | 1 |
| 10.2 | Function 10.2: Implement Fairino SDK adapter/Fairino API client on edge server | Simple | 1 |
| 10.3 | Function 10.3: Receive commands/configuration from cloud and kiosk | Simple | 1 |
| 10.4 | Function 10.4: Execute robot order workflow locally through order executor | Simple | 1 |
| 10.5 | Function 10.5: Implement safety monitor for emergency stop and sensor conditions | Simple | 1 |
| 10.6 | Function 10.6: Maintain local queue/cache for offline or unstable Internet scenarios |  |  |
| 10.7 | Function 10.7: Upload telemetry, logs, and status to cloud |  |  |
| 10.8 | Function 10.8: Support recovery flow when robot action or dispenser action fails |  |  |
| 11 | Feature 11: Monitoring, Alerts & Notifications |  | 5 |
| 11.1 | Function 11.1: Monitor kiosk, robot, dispenser, sensor, and inventory status in real time | Simple | 1 |
| 11.2 | Function 11.2: Generate alerts for low ingredients, device error, robot failure, payment issue, and refrigeration issue | Simple | 1 |
| 11.3 | Function 11.3: Send notifications to staff/manager through dashboard or mobile app | Simple | 1 |
| 11.4 | Function 11.4: View logs and telemetry for trouble shooting | Simple | 1 |
| 11.5 | Function 11.5: Track order queue and robot preparation progress | Simple | 1 |
| 12 | Feature 12: Reports & Business Management |  | 5 |
| 12.1 | Function 12.1: View sales, revenue, order, and kiosk performance reports | Simple | 1 |
| 12.2 | Function 12.2: View inventory and ingredient consumption reports | Simple | 1 |
| 12.3 | Functions 12.3: View popular flavour/topping/product reports | Simple | 1 |
| 12.4 | Functions 12.4: Tract location owner revenue or commission | Simple | 1 |
| 12.5 | Functions 12.5: Export basic operational reports for manager/admin | Simple | 1 |
| 13 | Feature 13: Deployment, Security & Configuration |  | 8 |
| 13.1 | Function 13.1: Prepare cloud deployment for backend API, database, cache, and monitoring | Simple | 1 |
| 13.2 | Function 13.2: Configure PostgreSQL database primary data store and Redis cache/session/queue support | Simple | 1 |
| 13.3 | Function 13.3: Configure HTTPS, environment variable, and secure secret storage | Simple | 1 |
| 13.4 | Function 13.4: Set up CI/CD pipeline for backend, web dashboard, and mobile/kiosk builds | Simple | 2 |
| 13.5 | Function 13.5: Implement API security, encrypted communication, and device authentication design | Simple | 1 |
| 13.6 | Function 13.5: Prepare deployment documentation and rollback pan | Simple | 2 |
| 14 | Feature 14: Testing, QA & Documentation |  | 26 |
| 14.1 | Function 14.1: Unit testing for business logic and service modules | Medium | 4 |
| 14.2 | Function 14.2: Integration testing for API, database, Redis, payment, and device communication | Complex | 16 |
| 14.3 | Function 14.3: System testing for complete order-to-robot workflow | Medium | 2 |
| 14.4 | Function 14.4: Prepare user guide, admin manual, technical document, and deployment guide | Medium | 2 |
| 14.5 | Function 14.5 Final report, presentation, and demonstration preparation | Medium | 2 |
| … | … | … | … |
| Total Estimated Effort (man-days) |  |  | 108 |

### 1.2 Project Objectives

- The purpose of this project is to develop IceBot, a smart multi-location automated ice cream vending system that improves operational efficiency and customer experience through software, robotics, IoT, and cloud management. Key objectives include:

- Providing administrators and managers with a web dashboard to manage organizations, locations, kiosk, products, workflows, users, permissions, orders, inventory, alerts, and reports.

- Allowing customers to browse products, customize ice cream, make digital payments, track order, status, and receive ice cream served automatically by a robotic arm.

- Enabling staff to monitor assigned kiosks, receive machine alerts, refill ingredients, reports issues, and perform basic maintenance

- Building an edge gateway that can receive order commands, coordinate the Fairino robotic arm and field devices, monitor safety conditions, cache tasks locally, and upload telemetry to the cloud.

- Supporting scalable deployment across multiple high-traffic locations with centralized monitoring and configuration synchronization

### 1.3 Project Timeframe

- The project is scheduled to be completed within 3 months (from May 2026 to August 2026). The timeline covers requirement analysis, project planning, system architecture design, implementation, robot and IoT integration, testing, deployment preparation, documentation, user training, and final demonstration.

### 1.4 Project Success Criteria

- SMART Goal 1: 100% of deployed kiosks will operate with the embedded ordering app and perform automatic workflow without manual intervention.

- SMART Goal 2: 100% of administrators and organization admins can fully manage workflow, product, kiosk, devices and order history from the admin dashboard.

- SMART Goal 3: At least 90% of users (admins and customers) will rate the system as helpful and reliable service quality and speed.

### 1.5 Project Customer/Sponsor

- The primary sponsor of this project is UniGroup, providing  financial support for devices.

- The target customers are individuals who wish to purchase ice cream quickly and conveniently through smart vending machines. These customers are typically located in small-to-medium businesses, coworking spaces, office buildings, and public areas.

### 1.6 Project Constraint

- Cost: ≈ 400.000.000 VND (IoT Devices).

- Resources: The project team consists of 5 developers and 1 mentor.

### 1.7 Project Quality

| # | Testing Stage | Test Coverage | No. of Defects | % of Defect | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Reviewing | 100% | 2 | 5% | Tracking documents, logic |
| 2 | Unit Test | 95% | 3 | 7% | Using xUnit, TestContainer, Respawner |
| 3 | Integration Test | 90% | 4 | 10% | Tracking API between each modules |
| 4 | System Test | 95% | 2 | 5% | End-to-end with tester |
| 5 | Acceptance Test | 100% | 1 | 3% | UAT by customer |

### 1.8 Project Milestone Timeliness

- The project follows the Agile software development model and is structured into eight sprints:

1. Project initiation

2. Sprint 1: Planning and Setup (14 man-days)

3. Sprint 2: (14 man-days)

4. Sprint 3: (14 man-days)

5. Sprint 4: (14 man-days)

6. Sprint 5: (14 man-days)

7. Sprint 6: (14 man-days)

8. Sprint 7: (14 man-days)

9. Sprint 8: Release and Deployment (14 man-days)

### 1.9 Project Risks

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | IoT devices malfunction or hardware damage (e.g., broken dispenser, motor failure) | High | Medium | Maintain spare parts, set up hardware health monitoring, prepare on-site troubleshooting guides. |
| 2 | IoT devices are bulky and difficult to transport for testing or demo. | Medium | High | Develop a virtual simulation model of the system to conduct remote demos and functional testing. |
| 3 | Cloud-edge communication is unstable due to network issue at kiosk location | High | Medium | Use local queue/cache on edge server, retry mechanism |

## 2. Management Approach

### 2.1 Project Process

- The project adopts a pure Agile methodology to ensure continuous collaboration, rapid delivery, and high adaptability to changing requirements and is structured into eight sprints:

1. Project initiation:

1.1 Define project scope and objectives

1.2 Identify stakeholders and their requirements

1.3 Create project charter

1.3.1 Define project scope and objectives

1.4 Define project team roles and responsibilities

1.5 Conduct project kickoff meeting

2. Sprint 1: Planning and Setup (14 man-days)

2.1 Create product backlog and prioritize features

2.2 Define sprint cycles and timelines

2.3 Setup development environment and tools

2.4 Define definition of done (DoD)

2.5 Develop release plan

3. Sprint 2: (14 man-days)

3.1 Sprint planning meeting

3.2 Develop user stories for sprint

3.3 Define sprint backlog and tasks

3.4 Develop software architecture and design

3.5 Implement core functionalities of Automatic Brewing Coffee System

3.6 Conduct daily scrum meetings

3.7 Test and validate sprint deliverables

3.8 Conduct sprint review and retrospective

4. Sprint 3: (14 man-days)

4.1 Sprint planning meeting

4.2 Develop user stories for sprint

4.3 Define sprint backlog and tasks

4.4 Develop software architecture and design

4.5 Implement core functionalities of Automatic Brewing Coffee System

4.6 Conduct daily scrum meetings

4.7 Test and validate sprint deliverables

4.8 Conduct sprint review and retrospective

5. Sprint 4: (14 man-days)

5.1 Sprint planning meeting

5.2 Develop user stories for sprint

5.3 Define sprint backlog and tasks

5.4 Develop software architecture and design

5.5 Implement core functionalities of Automatic Brewing Coffee System

5.6 Conduct daily scrum meetings

5.7 Test and validate sprint deliverables

5.8 Conduct sprint review and retrospective

6. Sprint 5: (14 man-days)

5.1 Sprint planning meeting

5.2 Develop user stories for sprint

5.3 Define sprint backlog and tasks

5.4 Develop software architecture and design

5.5 Implement core functionalities of Automatic Brewing Coffee System

5.6 Conduct daily scrum meetings

5.7 Test and validate sprint deliverables

5.8 Conduct sprint review and retrospective

7. Sprint 6: (14 man-days)

5.1 Sprint planning meeting

5.2 Develop user stories for sprint

5.3 Define sprint backlog and tasks

5.4 Develop software architecture and design

5.5 Implement core functionalities of Automatic Brewing Coffee System

5.6 Conduct daily scrum meetings

5.7 Test and validate sprint deliverables

5.8 Conduct sprint review and retrospective

8. Sprint 7: (14 man-days)

5.1 Sprint planning meeting

5.2 Develop user stories for sprint

5.3 Define sprint backlog and tasks

5.4 Develop software architecture and design

5.5 Implement core functionalities of Automatic Brewing Coffee System

5.6 Conduct daily scrum meetings

5.7 Test and validate sprint deliverables

5.8 Conduct sprint review and retrospective

9. Sprint 8: Release and Deployment (14 man-days)

6.1 Conduct final sprint planning meetings

6.2 Test and validate release

6.3 Conduct final sprint review and retrospective

6.4 Deploy Automatic Brewing Coffee System to product environment

6.5 Conduct post-release testing and monitoring

6.6 Close out project

### 2.2 Quality Management

#### 2.2.2 Quality Assurance

| Title | Purpose | When | How |
| --- | --- | --- | --- |
| Process To Manage Bugs | Ensure that identified bugs are documented, tracked, and resolved efficiently. | Throughout the development and testing phases. | Use a bug-tracking tool (e.g., Trello) where developers, testers, and stakeholders log bugs. Categorize bugs by priority and assign them to appropriate team members with deadlines for resolution. |
| Process For Change Requests | Manage requested changes to ensure they are reviewed, prioritized, and implemented without disrupting the project | When any new requirement or modification arises during the project | Define a clear CR workflow: submit a request → analyze impact → approve/reject → implement → verify changes. Use tools like Confluence or custom workflows to document the process |
| Process Design for Basic Design | Ensure that the basic design phase follows a structured approach, minimizing errors in initial requirements and design stages. | During the initial design phase | Use collaborative tools for documentation (e.g., DrawIO, Figma) and conduct peer reviews of design documents to validate alignment with project requirements. |
| Code Review Process | Identify and resolve issues in the codebase early to maintain coding standards and prevent defects. | During the development phase, before any module is merged into the main branch. | Implement a peer-review system where developers review each other's code using version control platforms (e.g., GitHub). Create a checklist to evaluate code for functionality, security, and adherence to coding standards. |
| Requirement Validation Workshops | Ensure all project requirements are clearly understood and agreed upon by stakeholders. | Before the design and development phases begin. | Organize sessions with students, faculty, and administrators to review and validate the gathered requirements. Record feedback and incorporate necessary adjustments into the final requirements document. |

#### 2.2.3 Quality Control

| Title | Purpose | When | How |
| --- | --- | --- | --- |
| IT Test Implementation | Verify that system modules function correctly under simulated conditions | After individual module development. | Perform integration testing by combining modules and testing their interactions using testing tools like xUnit and TestContainer. |
| ST Test Implementation | Test the system as a whole to ensure it meets functional and non-functional requirements. | After all modules are integrated. | Execute system tests to validate user workflows, performance, and scalability, logging results for any failed cases. |
| UAT Test Implementation | Validate that the system meets end-user requirements and expectations. | Validate that the system meets end-user requirements and expectations. | Conduct sessions with a representative group of students and mentor to test the system in a simulated real-world environment. Gather feedback and resolve critical issues before launch |
| Regression Testing | Ensure new code changes do not negatively impact existing functionalities. | After every significant update or bug fix. | Run a suite of automated or manual tests covering previously working features. Use testing tools like TestContainer and xUnit |
| UI/UX Validation | Confirm that the user interface and experience are intuitive and meet design standards. | During system testing and UAT. | Use heuristic evaluation techniques and involve designers and end-users to assess the system for usability, accessibility, and consistency. |
| Hardware/Robot Safety Test | Ensure robot arm and field devices operate safely | Before robot execution demo and final presentation | Check emergency stop, sensor status, command limits, safe movement area, retry behaviour, and unavailable state handling |

### 2.3 Training Plan

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| C#, ASP.NET Core | TuanTH, HungVN, TrungDLT, KietCT | Daily | Mandatory |
| Typescript, NextJS | TrungDLT, ThuanTQ | Daily | Mandatory |
| Dart, Flutter | TrungDLT, ThuanTQ | Daily | Mandatory |
| IoT Device Functionality | KietCT, TuanTH, HungVN, TrungDLT | Daily | Mandatory |
| IoT Device Communication Protocol | KietCT, TrungDLT, HungVN | Daily | Mandatory |
| Linux Platform | TuanTH, KietCT | Weekly | Mandatory |
| Git, Github | KietCT, TrungDLT, HungVN, TuanTH, ThuanTQ | Daily | Mandatory |
| Trello | KietCT, TrungDLT, HungVN, TuanTH, ThuanTQ | Daily | Mandatory |
| Docker | KietCT, TrungDLT, HungVN, TuanTH | Weekly | Mandatory |
| Deployment IIS (VPS) | TuanTH | Monthly | Mandatory |

## 3. Project Deliverables

| # | Deliverable | Due Date | Notes |
| --- | --- | --- | --- |
| 1 | User-friendly Administrator Management Webapp (Server) | 1/8/2026 | A fully functional and intuitive web platform accessible to system admin and organization admin for tracking kiosks, devices, products workflows, and managing orders. |
| 2 | Mobile Android Application (Kiosk) | 8/8/2026 | Android mobile app working perfectly on tablet in kiosk to provide access to the make transaction include view products, add to cart, checkout, view orders and hot-setting for devices with admin permission. |
| 3 | IceBot System (Kiosk) | 16/8/2026 | A system that functions as an orchestrator, coordinating all devices within the kiosk to ensure they operate smoothly and cohesively. |
| 4 | Documents, Reports and Training Materials | 22/8/2026 | Comprehensive user manuals, system documentation and training modules for end-users. |

## 4. Responsibility Assignments

D~Do; R~Review; S~Support; I~Informed; <blank>- Omitted

| Responsibility | TuanTH SE151518 | KietCT SE150863 | TrungDLT SE183054 | HungVN SE173374 | ThuanTQ SE182998 | PhuongLHK |
| --- | --- | --- | --- | --- | --- | --- |
| Project Planning & Tracking | D | I | S | S | I | R, I |
| Prepare Project Introduction Document | D | I | S | S | I | R, I |
| Prepare SRS Document (Overview Part) | D | I | S | S | I | R, I |
| Prepare SRS Document (User Requirements) | D | S | S | S | S | R, I |
| Design System Architecture (API, IoT, Cloud) | S | S | S | D | I | R, I |
| Develop Backend (ASP.NET Core) | S | S | S | D | I | R, I |
| Develop Frontend (Next.js Admin Portal) | I | I | S | I | D | R, I |
| Backend Kiosk Cloud Services and Deployment (Azure IoT Hub, Cloudflare, Docker) | S | D | S | S | I | R, I |
| Webapp Deployment (Vercel) | D | I | S | S | S | R, I |
| Backend Server Cloud Services and Deployment (IIS, VPS, Docker) | D | S | S | S | I | R, I |
| Develop Backend Kiosk (ASP.NET Core) | S | D | S | S | I | R, I |
| Develop Tablet App Kiosk | I | I | D | I | S | R, I |
| Develop Mobile App for Staff | I | I | D | I | S | R, I |
| IoT Devices Cable Communication Protocol | I | D | S | S | I | R, I |
| Project Management Plan | D | I | S | S | I | R, I |

## 5. Project Communications

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Integrate payment service | PayOS | Integrate their payment service into AutoBrewingCoffee | Daily | Offline meeting |
| Project progress update | UniGroup | Keep informed about progress | Weekly | Report face-to-face |
| User Guides and Updates | Admin (Sys & Org) | Ensure effective system use | Monthly | Documentation, video |
| Final presentation preparation | All team members | Prepare capstone defense, demoflow, backup plan, and Q&A material | Final month | Slide, Demos, Rehearsal |

## 6. Configuration Management

### 6.1 Document Management

- All project documents, including requirement specifications, test plans, architecture diagrams, and user manuals, will be centrally stored and managed using Google Drive. Version control is maintained through logging on record of changes.

- Each document change is reviewed and approved by all the team members and mentors. Access control ensures that only authorized personnel can edit documents while allowing team-wide read-only access to ensure alignment and transparency.

- Weekly backups will be performed to prevent data loss, and outdated documents will be archived into a designated folder to reduce clutter and ensure traceability.

### 6.2 Source Code Management

- The source code is managed through Git and hosted on GitHub under a private repository. A Git Flow branching model is adopted with the following structure:

- main: stable release versions

- develop: current sprint development

- dev/feat/*: new feature branches

- dev/test/*: new test branches

- bugfix/*: fixes for in-sprint defects

- hotfix/*: urgent fixes post-deployment

- deploy/*: deployment ci/cd

- All code changes must go through Pull Requests (PRs) with peer reviews and CI pipeline checks before being merged. Automated build and test processes are integrated via GitHub Actions to ensure code quality and fast feedback.

- Each release will be tagged (e.g., v1.0.0) with a changelog entry to track features, fixes, and improvements. Code backup and rollback strategies are in place to ensure recovery in case of failure.

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | NextJS (FrontEnd), Flutter (App), C#/ASP.NET Core (BackEnd) |
| Database | PostgreSQL |
| IDEs/Editors | Visual Studio Code, Antigravity, Cursor, Visual Studio |
| Diagramming | DrawIO, SQL Server Diagram, yED |
| Documentation | Ms Office, Google Docs/Sheets, Canva |
| Version Control | Github (Source Codes), Google Drive (Documents) |
| Deployment server | Vercel, Docker |
| Project management | Trello (Schedule, Tasks) |
| Payment Integration | PayOS |
| IoT Platform | Raspberry Pi |
| Cache Database | Redis |
| Web Security & CDN | Cloudflare |